## Apr 19 2022
Test Case Plan
2022-04-18
# | Functionality | Scenario | Description | Notes | Tested by | Android 10.0 (Pixel 2 Emulator) | Android 11.0 (Pixel 2 Emulator) | Android 12.0 (Pixel 2 Emulator)
1 | Startup | App loads | All formating loads as expected |  | Nick | Passed | Passed | Passed
2 | API | API loads information | The Cat API is connected to the application | Not yet implemented | Nick | Failed | Failed | Failed
3 | JSON Object | JSON works correctly | Program is able to access CatAPI and return a JSOn Object containng cat info | Not yet implemented | Tartil | Failed | Failed | Failed
4 | Spinner | Spinner of Cat breeds | The spinner shows all of the cat breeds from the API | Not yet implemented | Tartil | Failed | Failed | Failed
5 | Selection | Select a Cat Breed | User is able to select a cat breed and selection properly loads in bottom fragment | Not yet implemented | Tami | Failed | Failed | Failed
6 | Image | Cat image | Cat image of user's selection shows in the bottom fragment | Not yet implemented | Nick | Failed | Failed | Failed
7 | Name | Cat name | Selected cat's name is dispalyed in bottom fragment | Not yet implemented | Nick | Failed | Failed | Failed
8 | Origin | Cat Origin | Selected cat's origin is dispalyed in bottom fragment | Not yet implemented | Tami | Failed | Failed | Failed
9 | Description | Cat decsription | Selected cat's descriptiom is dispalyed in bottom fragment | Not yet implemented | Tartil | Failed | Failed | Failed
10 | Temperament | ` | Selected cat's temperament is dispalyed in bottom fragment | Not yet implemented | Tartil | Failed | Failed | Failed

## Apr 20 2022
Test Case Plan
2022-04-20
# | Functionality | Scenario | Description | Notes | Tested by | Android 10.0 (Pixel 2 Emulator) | Android 11.0 (Pixel 2 Emulator) | Android 12.0 (Pixel 2 Emulator)
1 | Startup | App loads | All formating loads as expected |  | Nick | Passed | Passed | Passed
2 | API | API loads information | The Cat API is connected to the application | Not yet implemented | Nick | Passed | Passed | Passed
3 | JSON Object | JSON works correctly | Program is able to access CatAPI and return a JSOn Object containng cat info | Not yet implemented | Tartil | Passed | Passed | Passed
4 | Spinner | Spinner of Cat breeds | The spinner shows all of the cat breeds from the API | Not yet implemented | Tartil | Passed | Passed | Passed
5 | Selection | Select a Cat Breed | User is able to select a cat breed and selection properly loads in bottom fragment | Not yet implemented | Tami | Passed | Passed | Passed
6 | Image | Cat image | Cat image of user's selection shows in the bottom fragment | Not yet implemented | Nick | Failed | Failed | Failed
7 | Name | Cat name | Selected cat's name is dispalyed in bottom fragment | Not yet implemented | Nick | Failed | Failed | Failed
8 | Origin | Cat Origin | Selected cat's origin is dispalyed in bottom fragment | Not yet implemented | Tami | Failed | Failed | Failed
9 | Description | Cat decsription | Selected cat's descriptiom is dispalyed in bottom fragment | Not yet implemented | Tartil | Failed | Failed | Failed
10 | Temperament | Cat temperament | Selected cat's temperament is dispalyed in bottom fragment | Not yet implemented | Tartil | Failed | Failed | Failed

## Apr 21 2022
Test Case Plan
2022-04-21
# | Functionality | Scenario | Description | Notes | Tested by | Android 10.0 (Pixel 2 Emulator) | Android 11.0 (Pixel 2 Emulator) | Android 12.0 (Pixel 2 Emulator)
1 | Startup | App loads | All formating loads as expected |  | Nick | Passed | Passed | Passed
2 | API | API loads information | The Cat API is connected to the application | Not yet implemented | Nick | Passed | Passed | Passed
3 | JSON Object | JSON works correctly | Program is able to access CatAPI and return a JSOn Object containng cat info | Not yet implemented | Tartil | Passed | Passed | Passed
4 | Spinner | Spinner of Cat breeds | The spinner shows all of the cat breeds from the API | Not yet implemented | Tartil | Passed | Passed | Passed
5 | Selection | Select a Cat Breed | User is able to select a cat breed and selection properly loads in bottom fragment | Not yet implemented | Tami | Passed | Passed | Passed
6 | Image | Cat image | Cat image of user's selection shows in the bottom fragment | Not yet implemented | Nick | Passed | Passed | Passed
7 | Name | Cat name | Selected cat's name is dispalyed in bottom fragment | Not yet implemented | Nick | Passed | Passed | Passed
8 | Origin | Cat Origin | Selected cat's origin is dispalyed in bottom fragment | Not yet implemented | Tami | Passed | Passed | Passed
9 | Description | Cat decsription | Selected cat's descriptiom is dispalyed in bottom fragment | Not yet implemented | Tartil | Passed | Passed | Passed
10 | Temperament | Cat temperament | Selected cat's temperament is dispalyed in bottom fragment | Not yet implemented | Tartil | Passed | Passed | Passed